## Sheet1
Project Name | Status | % Complete | Notes | Requesting Dept | Deadline | % budget spent | RAG
Project 1 | Initiating | 0 | Initiation phase of the project. | Libraries | 2024-08-30 17:00 | 0 | Green
Project 2 | Executing | 60 | On - track No high or extreme risks have been registered | ICTS | 2024-10-31 | 0 | Green
Project 3 | Initiating | 14 | On-track Risks: No high or extreme risks / issues are registered | Registrar | 2025-03-28 17:00 | 0.20111 | Green
Project 4 | Executing/Delayed | 89 | This project is pending prioritisation from the eRA Working Group. | RO | 2024-08-31 | 0 | Yellow
Project 5 | Executing | 90 | On - track No high or extreme risks / issues are registered. | CILT | 2024-12-31 17:00 | 0.83592 | Green
Project 6 | Executing | 45 | Phase 1: Go-live of the short course certificates planned for 6 August 2024. Phase 2 : Deployment of digital and printed certificates for mainstream qualifications is underway: No high or extreme risks / issues are registered​. | Registrar | 2025-03-31 | 0 | Green
Project 7 | Executing | 12 | On - track | FIN | 2024-12-31 | 0 | Green
Project 8 | Executing | 89 | On - track No high or extreme risks / issues are registered. | RO | 2024-12-14 | 0.71604 | Green
Project 9 | Initiating | 0 | Awaiting BRS of preferred solution from HR who have met with UKZN to benchmark their solution. Implementation period ascertained once BRS received | HR | 2025-02-28 | 0 | Yellow
Project 10 | Executing | 60 | On - track No high or extreme risks / issues are registered. | CMD | 2024-08-31 | 0 | Green
Project 11 | Executing | 10 | On - Track | ICTS | 2024-08-31 | 0 | Green
Project 12 | Planning | 5 | On -Track. No budget assigned | CILT | 2024-09-28 | 0 | Green
Project 13 | Executing | 55 | P&S Owned | P & S | 2024-12-29 | 0.39826 | Green
Project 14 | Executing | 1.95 | The project is AMBER due to unavailability of key resources integral to completing the required analysis for the project. | ICTS | 2024-12-20 | 0 | Yellow
Project 15 | Planning | 55 | IT DR Plan and Governance workstreams are in progress The Project Charter is being reworked, and will be tabled at the next PSC. The project is AMBER until a revised end date is agreed with the PSC. No high or extreme risks / issues are registered​. | ICTS | 2024-06-30 | 0.038763 | Red
Project 16 | Initiating/ On Hold | 0 | This project is On hold, to release resources and capacity for the Digital Certificates Project (PRJ0017878), which is a higher priority. | ICTS | 2024-03-29 17:00 | 0 | Yellow
Project 17 | Initiating | 0 | Newly registered project | ICTS | 2029-01-31 17:00 | 0 | Green
Project 18 | Executing | 35 | On - track. No budget assigned Sites complete: 35% successfully configured Risks: No high or extreme risks / issues are registered | ICTS | 2025-06-30 | 0 | Green
Project 19 | Closing | 99 | All installations and configurations completed by December 2022. The final closure report has been drafted, pending sign-off of the Blue Print before the project will be closed complete. | ICTS | 2022-12-30 | 0.95
Project 20 | Executing | 50 | On - track | ICTS | 2024-09-06 17:00 | 0 | Green
Project 21 | Initiating | 20 | On-Track. No funding assigned | Science | 2025-01-31 | 0 | Green
Project 22 | Executing | 85 | On - track | RO | 2024-12-31 17:00 | 0 | Green
Project 23 | Initiating | 0 | Initiation Phase : Project Charter Review in progress | ICTS | 2024-11-29 17:00 | 0 | Green
Project 24 | Executing | 99 | Project tasks are completed, with the exception of the closure report to be drafted for distribution to PSC in August 2024. | ICTS | 2023-06-30 | 0.982
Project 25 | Planning | 50 | The Storage Renewal Project, has delivered the across data centre active-active storage capability. The project will leverage this functionality for selected IT systems. Status AMBER until a new revised end date to be provided in consultation with the sponsor No high or extreme risks / issues are registered​. | ICTS | 2024-06-30 | 0 | Yellow
Project 26 | Executing | 65 | On - track No high or extreme risks / issues are registered. | ICTS | 2024-08-30 17:00 | 0 | Green
Project 27 | Executing | 70 | On - track No high or extreme risks have been registered | ICTS | 2024-12-12 | 0.93835 | Green
Project 28 | Proposal/ On hold | 5 | Draft BRS completed and sent to Business stakeholders for review | DSA | 2022-04-14 17:00 | 0 | Yellow
Project 29 | Initiating/ On Hold | 5 | SAP Finance have other higher priorities. | FIN | 2024-12-31 17:00 | 0 | Yellow
Project 30 | Executing | 15 | On-Track. Steercom meeting re-scheduled for 5 August 2024 | ICTS | 2025-07-31 11:12 | 0.14704 | Green
Project 31 | Executing | 30 | Audit of UCT Microsoft Licenses completed Initial phase of identifying Office Activated Users Official communications sent to the campus community about the changes to Microsoft Licenses | ICTS | 2025-06-30 | 0 | Green
Project 32 | Initiating/ On Hold | 0 | GRC Manager has been assigned as Project Manager, and is in the process of reviewing the requirements, scope, and approach to restart the project. | ICTS | 2024-05-31 17:00 | 0 | Yellow
Project 33 | Initiating | 10 | On - Track | Commerce | 2024-08-20 13:01 | 0 | Green